## Gantt Chart
All the Metadata’s a Stage: Exploratory Data Analysis of British Comedy Dramas Across 17th-19th Centuries
PROJECT BACKGROUND |  | PROJECT MANAGER |  | START DATE | END DATE | [14 empty] | PROJECT DURATION
Execution of an 8-week digital curation lifecycle for the British Library Drama Dataset. |  | Chahna Ahuja |  | 2025-12-08 | 2025-01-05 | [14 empty] | 28 DAYS
Real start date is 8 December 2025, Monday
PHASE | TASK NAME | START DATE | FINISH DATE | PERCENTAGE COMPLETE | 2025-12-08 | [6 empty] | 2025-12-15 | [6 empty] | 2025-12-22 | [6 empty] | 2025-12-29 | [6 empty] | 2026-01-05
[5 empty] | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa
1 | Dataset Exploration and Preliminary RQs | 2025-12-08 | 2025-12-14 | 100%
1.1 | Explore Dataset on OpenRefine | 2025-12-08 | 2025-12-08 | 100% | bar: 2025-12-08 M
1.2 | Read and Annotate Literature | 2025-12-09 | 2025-12-11 | 100% | bar: 2025-12-08 T to 2025-12-08 R
1.3 | Formulate Preliminary RQS | 2025-12-12 | 2025-12-13 | 100% | bar: 2025-12-08 F to 2025-12-08 Sa
2 | Defining Methods | 2025-12-15 | 2025-12-18 | 100%
2.1 | bar: 2025-12-15 Su to 2025-12-15 Sa; 2025-12-29 Su to 2025-12-29 Sa
2.2 | bar: 2025-12-15 Su to 2025-12-15 Sa; 2025-12-29 Su to 2025-12-29 Sa
2.3 | bar: 2025-12-15 Su to 2025-12-15 Sa; 2025-12-29 Su to 2025-12-29 Sa
2.4 | bar: 2025-12-15 Su to 2025-12-15 Sa; 2025-12-29 Su to 2025-12-29 Sa
2.5 | bar: 2025-12-15 Su to 2025-12-15 Sa; 2025-12-29 Su to 2025-12-29 Sa
2.6 | bar: 2025-12-15 Su to 2025-12-15 Sa; 2025-12-29 Su to 2025-12-29 Sa
2.7 | bar: 2025-12-15 Su to 2025-12-15 Sa; 2025-12-29 Su to 2025-12-29 Sa
2.8 | bar: 2025-12-15 Su to 2025-12-15 Sa; 2025-12-29 Su to 2025-12-29 Sa
2.9 | bar: 2025-12-15 Su to 2025-12-15 Sa; 2025-12-29 Su to 2025-12-29 Sa
2.10. | bar: 2025-12-15 Su to 2025-12-15 Sa; 2025-12-29 Su to 2025-12-29 Sa
2.1 | Read Literature for Methods | 2025-12-15 | 2025-12-16 | 100% | bar: 2025-12-15 M to 2025-12-15 T
2.2 | Explore Toy Examples with these methods | 2025-12-16 | 2025-12-17 | 100% | bar: 2025-12-15 T to 2025-12-15 W
2.3 | Finalize Methods | 2025-12-17 | 2025-12-18 | 100% | bar: 2025-12-15 W to 2025-12-15 R
MILESTONE 1 | Research Ideation |  |  | 100%
3 | Data Cleaning and Descriptive Statistics | 2025-12-19 | 2025-12-22 | 100%
3.1 | bar: 2025-12-15 Su to 2025-12-15 Sa; 2025-12-29 Su to 2025-12-29 Sa
3.2 | bar: 2025-12-15 Su to 2025-12-15 Sa; 2025-12-29 Su to 2025-12-29 Sa
3.3 | bar: 2025-12-15 Su to 2025-12-15 Sa; 2025-12-29 Su to 2025-12-29 Sa
3.4 | bar: 2025-12-15 Su to 2025-12-15 Sa; 2025-12-29 Su to 2025-12-29 Sa
3.5 | bar: 2025-12-15 Su to 2025-12-15 Sa; 2025-12-29 Su to 2025-12-29 Sa
3.6 | bar: 2025-12-15 Su to 2025-12-15 Sa; 2025-12-29 Su to 2025-12-29 Sa
3.7 | bar: 2025-12-15 Su to 2025-12-15 Sa; 2025-12-29 Su to 2025-12-29 Sa
3.8 | bar: 2025-12-15 Su to 2025-12-15 Sa; 2025-12-29 Su to 2025-12-29 Sa
3.9 | bar: 2025-12-15 Su to 2025-12-15 Sa; 2025-12-29 Su to 2025-12-29 Sa
3.10. | bar: 2025-12-15 Su to 2025-12-15 Sa; 2025-12-29 Su to 2025-12-29 Sa
3.1 | Load and Inspect Data in Python | 2025-12-19 | 2025-12-19 | 100% | bar: 2025-12-15 F
3.2 | Clean Consitencies in OpenRefine (Parallel) | 2025-12-19 | 2025-12-20 | 100% | bar: 2025-12-15 F to 2025-12-15 Sa
4.1
4.2
4.3
4.4
4.5
4.6
4.7
4.8
4.9
4.10.
3.3 | Questions for Descriptive Statistics | 2025-12-20 | 2025-12-20 | 100% | bar: 2025-12-15 Sa
3.4 | Code snippets for questions with visualizations | 2025-12-21 | 2025-12-22 | 100% | bar: 2025-12-22 Su to 2025-12-22 M
4 | Data Enrichment | 2025-12-23 | 2025-12-24 | 100%
4.1 | Code for enriching data through wikidata | 2025-12-23 | 2025-12-24 | 100% | bar: 2025-12-22 T to 2025-12-22 W
MILESTONE 4 | Final Delivery | 2025-12-07 | 2025-12-07 | 100% | bar: 2025-12-15 Su; 2025-12-22 Su; 2025-12-29 Su; 2026-01-05 Su
17.1 | bar: 2025-12-15 Su; 2025-12-22 Su; 2025-12-29 Su; 2026-01-05 Su
17.2 | bar: 2025-12-15 Su; 2025-12-22 Su; 2025-12-29 Su; 2026-01-05 Su
17.3 | bar: 2025-12-15 Su; 2025-12-22 Su; 2025-12-29 Su; 2026-01-05 Su
17.4 | bar: 2025-12-15 Su; 2025-12-22 Su; 2025-12-29 Su; 2026-01-05 Su
17.5 | bar: 2025-12-15 Su; 2025-12-22 Su; 2025-12-29 Su; 2026-01-05 Su
17.6 | bar: 2025-12-15 Su; 2025-12-22 Su; 2025-12-29 Su; 2026-01-05 Su
17.7 | bar: 2025-12-15 Su; 2025-12-22 Su; 2025-12-29 Su; 2026-01-05 Su
17.8 | bar: 2025-12-15 Su; 2025-12-22 Su; 2025-12-29 Su; 2026-01-05 Su
17.9 | bar: 2025-12-15 Su; 2025-12-22 Su; 2025-12-29 Su; 2026-01-05 Su
5 | Exploratory Data Analysis | 2025-12-26 | 2025-12-28 | 100%
5.1 | Temporal Distribution | 2025-12-26 | 2025-12-26 | 100% | bar: 2025-12-22 F
5.2 | Spatial Distribution | 2025-12-27 | 2025-12-27 | 100% | bar: 2025-12-22 Sa
5.3 | Authorship Patterns | 2025-12-28 | 2025-12-28 | 100% | bar: 2025-12-29 Su
6 | Text Network Analysis | 2025-12-29 | 2025-12-31 | 100%
6.1 | Text preprocessing and tokenization | 2025-12-29 | 2025-12-29 | 100% | bar: 2025-12-29 M
6.2 | Exploratory Text Analysis | 2025-12-29 | 2025-12-30 | 100% | bar: 2025-12-29 M to 2025-12-29 T
6.3 | Code for Text Networks Python | 2025-12-31 | 2025-12-31 | 100% | bar: 2025-12-29 W
6.4 | Network Visualization In Gephi | 2025-12-31 | 2025-12-31 | 100% | bar: 2025-12-29 W
MILESTONE 2 | Analysis Delivery |  |  | 100%
7 | Interpretation for Report | 2026-01-01 | 2026-01-03 | 100%
7.1 | Review literature and draft interpretations | 2026-01-01 | 2026-01-02 | 100% | bar: 2025-12-29 R to 2025-12-29 F
7.2 | Write findings | 2026-01-02 | 2026-01-03 | 100% | bar: 2025-12-29 F to 2025-12-29 Sa
8 | Deliverables | 2025-01-04 | 2025-01-04 | 100% | bar: 2026-01-05 Su
8.1 | Format Report | 2025-01-04 | 2025-01-04 | 100% | bar: 2026-01-05 Su
8.2 | HTML Jupyter Notebook | 2025-01-04 | 2025-01-04 | 100% | bar: 2026-01-05 Su
8.3 | Github | 2025-01-04 | 2025-01-04 | 100% | bar: 2026-01-05 Su
8.4 | Peer Review | 2025-01-04 | 2025-01-04 | 100% | bar: 2026-01-05 Su
MILESTONE 3 | Final Delivery | 2025-01-05 | 2025-01-05 | 100%